## Test Cases
Module Name |  | Staff Information |  | Test Designed By | Sayak Bose |  | Test Designed Date |  | 2023-01-21
Test Title |  | Staff Information Page Checking |  | Test Execution Date | 8.2.23
Test Summary |  | To check if the Staff Information Page is working properly and designed correctly. |  | Test Executed By | Krittika Chakraborty
Prerequisite(s) |  | The user must have an existing account.
Dependencies |  | The Login and Home page must be working properly.
Test Case ID | Page Name | Action | Test Data | Expected Result | Actual Result | Test Browser | Test Result (Pass/Fail) | Comments | Defect Log/ID | Defect Status
TC_StaffInfo_001 | Staff Information Page | Trying to visit the page without logging in using the page's url. | Putting http://localhost:8080/proj1/depSelect.jsp and http://localhost:8080/proj1/StaffInfo.jsp?dep=information%20technology(it) in the url bar of google chrome. | The user should get redirected to login page. | The user gets redirected to login page | Google Chrome | pass
TC_StaffInfo_002 | Staff Information Page | Clicking on the NAAC menu in the nav bar |  | User should get a dropdown containing 'Reports'. | User gets a dropdown menu containing 'Reports' | Google Chrome | pass
TC_StaffInfo_003 | Staff Information Page | Clicking on 'Reports' under 'NAAC'. |  | User should get a dropdown containing 'Staff Information' option. | User gets a dropdown menu containing 'Staff Information' | Google Chrome | pass
TC_StaffInfo_004 | Staff Information Page | Selecting 'Staff Information' under 'Reports'. |  | The user should get redirected to Staff Information page. | User gets directed to the staff information page with a 'select department' button | Google Chrome | pass
TC_StaffInfo_005 | Staff Information Page | Checking if there is an option to select department at the top of the page with dropdown with values "ME","CE","ECE","CSE","EE","IT","AEIE","BBE","BCA","MCA","AI-ML" and "CSBS". |  | There should be an option to select department at the top of the page with dropdown with values "ME","CE","ECE","CSE","EE","IT","AEIE","BBE","BCA","MCA","AI-ML" and "CSBS". | Staff Information page has a button to select department with a dropdown menu containing all the department options | Google Chrome | pass
TC_StaffInfo_006 | Staff Information Page | There should be a banner at the top of the page like 'STAFF INFORMATION OF THE IT DEPARTMENT'. |  | There is a banner at the top of the page like 'STAFF INFORMATION OF THE IT DEPARTMENT'. | A banner on the top of page mentioning the name of the department as 'STAFF INFORMATION OF INFORMATION TECHNOLOGY' is shown | Google Chrome | pass
TC_StaffInfo_007 | Staff Information Page | Click on the select department option and select an department. | Click on the select department option and select IT. | The information present in mydetails table of the selected department should be shown in the screen. | A table appears containg all the information of the selected department | Google Chrome | pass
TC_StaffInfo_008 | Staff Information Page | Ther should be 10 columns in the page and the name of the columns should be correct. |  | There are be 10 columns in the page and the name of the columns are be correct. | There are be 10 columns in the page and the name of the columns are be correct. | Google Chrome | pass
TC_StaffInfo_009 | Staff Information Page | There should be no spelling or grammatical errors in the page. |  | There are no spelling or grammatical errors in the page. | There are no spelling or grammatical errors in the page. | Google Chrome | pass
TC_StaffInfo_010 | Staff Information Page | The font must be same for the entire Staff Information Page. |  | The font is same for the entire Staff Information Page. | The font is same for the entire Staff Information Page. | Google Chrome | pass
TC_StaffInfo_011 | Staff Information Page | In the Staff Information page only the info of the selected department should be present. | Click on the select department option and select IT. | In the Staff Information page only the info of the IT department is present. | In the Staff Information page only the info of the IT department is present. | Google Chrome | pass
TC_StaffInfo_012 | Staff Information Page | In the Staff Information page all the data present of the selected department should be shown. | Click on the select department option and select IT. | In the Staff Information page all the data present of the selected department should be shown. | In the Staff Information page all the data present of the selected department is shown. | Google Chrome | pass
TC_StaffInfo_013 | Staff Information Page | If the mydetails table is empty for an department then selecting that department should not show any data. | Click on the select department option and select CSBS. | In the StaffInfo page there is no data shown. | The Staff Information page of CSBS shows the banner mentioning the department and below that the table columns with no data written in the rows. | Google Chrome | pass | should show 'No Records'
TC_StaffInfo_014 | Staff Information Page | In the StaffInfo page First name, Midlle name and Last name should be displayed together under the column "Name". |  | In the StaffInfo page First name, Midlle name and Last name have been displayed together under the column "Name". | First name, Midlle name and Last name displayed together under the column "Name". | Google Chrome | pass
TC_StaffInfo_015 | Staff Information Page | clicking on Home button |  | The user should get redirected to Home page | Not working | Google Chrome | Fail |  | TC_SI_DEF01 | Not resolved
TC_StaffInfo_016 | Staff Information Page | clicking on Help button |  | User should get directed to the Help page | Not working | Google Chrome | Fail |  | TC_SI_DEF02 | Not resolved
TC_StaffInfo_017 | Staff Information Page | Clicking on Email-id on the top right corner | Click on email id | My details page opens | Not working | Google Chrome | Fail |  | TC_SI_DEF03 | Not resolved
TC_StaffInfo_018 | Staff Information Page | Submitting the my details form more than once by the same user should give error |  | Error page appears | Error page appears | Google Chrome | Pass
TC_StaffInfo_019 | Staff Information Page | There must be a home button on the error page |  | Home button should be there | Home button is there | Google Chrome | pass
TC_StaffInfo_020 | Staff Information Page | The home button on error page when clicked should redircect the user to the home page | Click on Home button | Redirects user to Home page | Redirects user to the home page | Google Chrome | pass

## Defects
Module Name | Test Case ID | Defect ID | Defect Description | Logged By | Logged Date | Defect Priority (High/Medium/Low) | Defect Fix Status | Resolved By | Resolution Date | Resolution Comments
Staff Information page | TC_StaffInfo_015 | TC_SI_DEF01 | Home button not working, when clicked should redirect the user to home page | Krittika Chakraborty | 9.2.23 | Medium | Not resolved
Staff Information page | TC_StaffInfo_016 | TC_SI_DEF02 | Help button not wokring, when clicked should direct the user to the help page | Krittika Chakraborty | 9.2.23 | Medium | Not resolved
Staff Information page | TC_StaffInfo_017 | TC_SI_DEF03 | clicking on email id on the top right corner doesn't redirect to the my details page | Krittika Chakraborty | 9.2.23 | Medium | Not resolved